Salesforce Enterprise Operations Monitoring Platform (SEOMP)

Implementation Plan

Author: VJ (Tomcodex)

Version: 1.0

Type: Enterprise Proof of Concept (POC) Implementation Plan

1. Purpose

This document defines the implementation plan for building the Salesforce Enterprise Operations Monitoring Platform (SEOMP). The plan translates the SEOMP concept into a phased execution roadmap covering architecture, development, testing, deployment, and operational readiness.

2. Project Goal

Build a real-time enterprise monitoring platform for Salesforce operations that provides:

Real-time system monitoring

Incident management with SLA tracking

Integration monitoring

Administrative workflow automation

Live dashboards and alerts

Multi-environment visibility across Dev, QA, and Prod

3. Scope

In Scope

Salesforce event generation using Platform Events or CDC

Node.js middleware on Heroku

Queue-based event processing using Kafka or Redis

PostgreSQL data storage

React or LWC dashboards

Slack and email alerting

CI/CD using GitHub Actions and Salesforce CLI

Terraform-based infrastructure setup

Out of Scope for Initial POC

Machine learning-based anomaly detection

Enterprise SSO beyond OAuth 2.0 and JWT

Complex ITSM integrations such as ServiceNow

Advanced auto-remediation beyond basic self-healing rules

4. Implementation Approach

The implementation will be delivered in phases so that core monitoring is operational early, followed by automation, reporting, and operational hardening.

Delivery Strategy

Phase 1: Foundation and architecture setup

Phase 2: Core event ingestion and incident tracking

Phase 3: Dashboard and alerting

Phase 4: SLA automation and self-healing features

Phase 5: Testing, deployment, and production readiness

5. Workstreams

5.1 Salesforce Workstream

Define custom objects:

Incident__c

Integration_Log__c

SLA_Policy__c

Environment__c

Deployment_Record__c

Audit_Trail__c

Configure Platform Events or Change Data Capture

Develop Flows for automation

Build Apex logic for event publishing and validations

Develop Lightning Web Components for internal dashboard views

5.2 Middleware Workstream

Create Node.js Express application

Implement Salesforce event subscription using Streaming API and CometD

Integrate Kafka or Redis for message buffering

Create processing services for incidents, logs, and metrics

Expose REST APIs:

POST /api/incidents

GET /api/incidents

POST /api/logs

GET /api/metrics

5.3 Data Workstream

Design PostgreSQL schema

Create tables for incidents, logs, environments, SLA policies, deployments, and audit records

Implement indexing for performance

Define retention and archival rules for logs

5.4 Dashboard Workstream

Build React dashboard or LWC dashboard

Display:

Health score

Incident count

API success rate

MTTR

Deployment status

Add WebSocket-based live updates

5.5 DevOps Workstream

Set up GitHub repository structure

Configure GitHub Actions pipeline

Run Apex validation tests

Run backend test suite

Deploy middleware to Heroku

Automate environment configuration using Terraform

6. Phase Plan

6.1 Phase 1: Foundation Setup

Objective

Establish project structure, environments, and base architecture.

Activities

Finalize architecture design

Create GitHub repositories or folders

Provision Heroku app

Provision PostgreSQL database

Set up Terraform configuration

Create Salesforce custom objects and fields

Set up local and sandbox development environments

Deliverables

Approved architecture diagram

Initialized codebase

Provisioned Heroku and PostgreSQL resources

Salesforce metadata baseline

Terraform scripts for infrastructure

6.2 Phase 2: Core Monitoring Build

Objective

Enable event ingestion, incident creation, and log persistence.

Activities

Configure Salesforce Platform Events or CDC

Implement Node.js subscriber using CometD

Push events to Kafka or Redis

Process events and store records in PostgreSQL

Create Incident__c records for failures

Capture API and integration logs

Deliverables

Working event pipeline

Stored incident and log data

Basic incident creation flow

Integration monitoring baseline

6.3 Phase 3: Dashboard and Alerting

Objective

Provide visibility into operational events and metrics.

Activities

Build metrics aggregation logic

Expose API endpoints for incident and metrics retrieval

Implement React or LWC dashboard

Add WebSocket live updates

Configure Slack and email notifications

Create dashboard widgets for key health indicators

Deliverables

Live operations dashboard

Alerting integration

Real-time metrics display

Incident monitoring view

6.4 Phase 4: SLA and Automation

Objective

Add workflow intelligence and operational automation.

Activities

Configure SLA policy mapping by severity

Track response and resolution timers

Auto-escalate breached incidents

Implement self-healing rule for repeated failures

Add audit trail logging for admin actions

Link incidents to runbook references

Deliverables

SLA engine

Escalation automation

Audit trail module

Initial self-healing capability

6.5 Phase 5: Production Readiness

Objective

Validate the platform and prepare it for demonstration or enterprise rollout.

Activities

Execute Apex unit tests

Run API and integration tests

Perform end-to-end validation across Sandbox, Staging, and Production-like environments

Review security controls

Complete deployment runbook

Conduct demo walkthrough and documentation review

Deliverables

Test results and validation report

Deployment checklist

Operational runbook

Final demo-ready SEOMP platform

7. Timeline

Suggested POC Timeline: 6 Weeks

Week 1

Architecture finalization

Environment setup

Data model creation

Week 2

Salesforce event configuration

Middleware project setup

Database schema creation

Week 3

Event ingestion and persistence

Incident creation logic

API implementation

Week 4

Dashboard development

Metrics aggregation

Slack and email alerts

Week 5

SLA engine

Audit logging

Self-healing automation

Week 6

Testing

Bug fixes

Deployment rehearsal

Final documentation and demo preparation

8. Roles and Responsibilities

Project Lead

Own delivery plan, scope, and stakeholder communication

Salesforce Developer

Build objects, Flows, Apex, and LWC components

Node.js Developer

Build middleware, APIs, queue processing, and WebSocket services

DevOps Engineer

Manage GitHub Actions, Heroku deployment, and Terraform

QA Engineer

Execute API, integration, and end-to-end testing

9. Dependencies

Salesforce sandbox or developer org

Heroku account and app access

PostgreSQL database access

GitHub repository access

Slack workspace or SMTP/email service for alerts

Kafka or Redis environment

10. Risks and Mitigation

Risk: Event delivery delays or failures

Mitigation: Use queue buffering and retry logic

Risk: Too many alerts causing noise

Mitigation: Add alert thresholds and severity-based routing

Risk: Data inconsistency between Salesforce and middleware

Mitigation: Add reconciliation jobs and audit logs

Risk: Deployment issues across environments

Mitigation: Use CI/CD validation and Terraform-based configuration

11. Success Criteria

The implementation will be considered successful if the platform can:

Capture Salesforce operational events in real time

Create and track incidents automatically

Store and visualize integration logs and metrics

Send alerts for critical failures

Display live operational dashboards

Support Dev, QA, and Prod environment monitoring

Demonstrate automated SLA tracking and escalation

12. Testing Plan

Apex unit tests for Salesforce logic

Backend API testing for all endpoints

Integration testing for event flow

Dashboard validation for live metrics

Security testing for authentication and access control

User acceptance demo for business and technical stakeholders

13. Deployment Plan

Deployment Path

Sandbox -> Staging -> Production

Deployment Steps

Validate metadata and backend code in lower environment

Run automated test suite

Deploy Salesforce changes

Deploy middleware to Heroku

Apply Terraform updates

Verify integrations, alerts, and dashboards

Complete smoke test

14. Handover Plan

Prepare technical documentation

Prepare architecture and data flow diagrams

Create runbook for alerts and incident handling

Record demo notes for interview or portfolio use

Share deployment steps and environment configuration details

15. Conclusion

This implementation plan provides a structured path to deliver SEOMP as an enterprise-style proof of concept. By following phased delivery, clear workstreams, and measurable success criteria, the project can demonstrate real-world Salesforce monitoring, automation, and operational management capabilities.